## Tula
Bill of Quantity for deep well drilling& construction Tula - LOT 2. A
Location
Zone: Sidama
Woreda : Dale
Kebele: Tula
Estimated depth 150m
No | Description | Unit | Qty | Unit price | Total price
1 | General item
1.1 | Mobilization of machineries , Equipment personal from Addis Abeba | km | 320
1.2 | Site clearing & rigging up prior to start drilling | ls | 1
2.1 | Drilling With Ǿ14"-Ǿ12"
2.2 | Drilling top part by Ǿ14" | M | 18
2.3 | Drilling in any formation by Ǿ12" Air DTH/Rotary Mud system | M | 132
3 | LOGGING
3.1 | Litho logic Logging | ls | 1
3.2 | Electrical Resistivity(long normal ,Short normal ,lateral | ls | 1 |  | Rate Only
4 | CONSTRUCTION
4.1 | Supply and installation
4.1.1 | Supply and installation of permanent steel casing for Ǿ 13 3/4" prevention of collapse | M | 18
4.1.2 | Supply and installation of Blind steel casing Ǿ 8 5/8" | M | 105
4.1.3 | Supply and installation of Screen steel casing Ǿ 8 5/8" | M | 45
4.1.4 | Supply and installation of ¾” class B observation pipe | M | 120
5 | Supply and pack river gravel (6-9mm diameter) | M3 | 18
6 | Well cleaning and development | Hr | 11
7 | Well head construction as per specification a concrete slab 0.5x0.5x0.50m (above ground) | ls | 1
8 | Grout the well up 6m depth 1;3 cement and sand mix | ls | 1
10 | PUMPING TEST
10.1 | Step drawdown test | Hr | 4
10.2 | Constant rate test | Hr | 72
10.3 | Recovery Monitoring | Hr | 24
11 | Chemical analysis | ls | 1
12 | Submit well completion report infives copies | ls | 1
TOTAL
VAT 15%
GRAND TOTAL
Notices:
- price of all material is calculated including transportation to the site
- point of borehole, working process and bore depth will be confirmed with clients expert/supervisor, who will be present in person during boring in the place
- client's supervisor may stop the drilling operations if in their opinion sufficient water supply has been obtained or further drilling is not promising for increasing the yield
- * works will be calculated according real amount (depth, quantity)

## Shoye
Bill of Quantity for deep well drilling& construction Wenenata - LOT 2. B
Zone: Sidama
Woreda :Dale
Kebele: Shoye
Estimated depth 170m
No | Description | Unit | Qty | Unit price | Total price
1 | General item
1.1 | inter site Mobilization of machineries , Equipment personal starting to Awaye adola Drilling site | km | 20
1.2 | Site clearing & rigging up prior to start drilling | Ls | 1
1.3 | Demobilization of Manpower and equipment after finshing Awaye adola site back to addis abeba | km | 320
2.1 | Drilling With Ǿ14"-Ǿ12"
2.2 | Drilling top part by Ǿ14" | M | 18
2.3 | Drilling in any formation by Ǿ12" Air DTH/Rotary Mud system | M | 152
3 | LOGGING
3.1 | Litho logic Logging | Ls | 1
3.2 | Electrical Resistivity(long normal ,Short normal ,lateral | Ls | 1 |  | Rate Only
4 | CONSTRUCTION
4.1 | Supply and installation
4.1.1 | Supply and installation of permanent steel casing for Ǿ 13 3/4" prevention of collapse | M | 18
4.1.2 | Supply and installation of Blind steel casing Ǿ 8 5/8" | M | 119
4.1.3 | Supply and installation of Screen steel casing Ǿ 8 5/8" | M | 51
4.1.4 | Supply and installation of ¾” class B observation pipe | M | 150
5 | Supply and pack river gravel (6-9mm diameter) | M3 | 20
6 | Well cleaning and development | Hr | 11
7 | Well head construction as per specification a concrete slab 0.5x0.5x0.50m (above ground) | ls | 1
8 | Grout the well up 6m depth 1;3 cement and sand mix | ls | 1
10 | PUMPING TEST
10.1 | Step drawdown test | Hr | 4
10.2 | Constant rate test | Hr | 72
10.3 | Recovery Monitoring | Hr | 24
11 | Chemical analysis | Ls | 1
12 | Submit well completion report in fives copies | Ls | 1
TOTAL
VAT 15%
GRAND TOTAL
Notices:
- price of all material is calculated including transportation to the site
- point of borehole, working process and bore depth will be confirmed with clients expert/supervisor, who will be present in person during boring in the place
- client's supervisor may stop the drilling operations if in their opinion sufficient water supply has been obtained or further drilling is not promising for increasing the yield
- * works will be calculated according real amount (depth, quantity)

## Woreta
Bill of Quantity for deep well drilling& construction Boreta - LOT 1. B Bill of Quantity for deep well drilling& construction Wenenata - LOT 2. B
Location
Zone: Sidama
Woreda : Bona Zuriya
Kebele: Boreta Woyo
Estimated depth 150m | [5 empty] | 150
No | Description | Unit | Qty | Unit price | Total price
1 | General item
1.1 | Inter site Mobilization of machineries , Equipment personal starting to awaye adola to drilling site | km | 50
1.2 | Site clearing & rigging up prior to start drilling | ls | 1
2.1 | Drilling With Ǿ14"-Ǿ12"
2.2 | Drilling top part by Ǿ14" | M | 18
2.3 | Drilling in any formation by Ǿ12" Air DTH/Rotary Mud system | M | 132
3 | LOGGING
3.1 | Litho logic Logging | ls | 1
3.2 | Electrical Resistivity(long normal ,Short normal ,lateral | ls | 1 |  | Rate Only
4 | CONSTRUCTION
4.1 | Supply and installation
4.1.1 | Supply and installation of permanent steel casing for Ǿ 13 3/4" prevention of collapse | M | 18
4.1.2 | Supply and installation of Blind steel casing Ǿ 8 5/8" | M | 105
4.1.3 | Supply and installation of Screen steel casing Ǿ 8 5/8" | M | 45
4.1.4 | Supply and installation of ¾” class B observation pipe | M | 120
5 | Supply and pack river gravel (6-9mm diameter) | M3 | 16
6 | Well cleaning and development | Hr | 11
7 | Well head construction as per specification a concrete slab 0.5x0.5x0.50m (above ground) | ls | 1
8 | Grout the well up 6m depth 1;3 cement and sand mix | ls | 1
10 | PUMPING TEST
10.1 | Step drawdown test | Hr | 4
10.2 | Constant rate test | Hr | 72
10.3 | Recovery Monitoring | Hr | 24
11 | Chemical analysis | ls | 1
12 | Submit well completion report in fives copies | ls | 1
TOTAL
VAT 15%
GRAND TOTAL
Notices:
- price of all material is calculated including transportation to the site
- point of borehole, working process and bore depth will be confirmed with clients expert/supervisor, who will be present in person during boring in the place
- client's supervisor may stop the drilling operations if in their opinion sufficient water supply has been obtained or further drilling is not promising for increasing the yield
- * works will be calculated according real amount (depth, quantity)

## Awaye adola
Bill of Quantity for deep well drilling& construction Awaye Adola - 1. A
Zone: Sidama
Woreda :Bona Zuriya
Kebele: Awaye adola
Estimated depth 170m
No | Description | Unit | Qty | Unit price | Total price
1 | General item
1.1 | Mobilization of machineries , Equipment personal starting to from addis abeba to Drilling site | km | 415
1.2 | Site clearing & rigging up prior to start drilling | ls | 1
2.1 | Drilling With Ǿ14"-Ǿ12"
2.2 | Drilling top part by Ǿ14" | M | 18
2.3 | Drilling in any formation by Ǿ12" Air DTH/Rotary Mud system | M | 152
3 | LOGGING
3.1 | Litho logic Logging | ls | 1
3.2 | Electrical Resistivity(long normal ,Short normal ,lateral | ls | 1 |  | Rate Only
4 | CONSTRUCTION
4.1 | Supply and installation
4.1.1 | Supply and installation of permanent steel casing for Ǿ 13 3/4" prevention of collapse | M | 18
4.1.2 | Supply and installation of Blind steel casing Ǿ 8 5/8" | M | 119
4.1.3 | Supply and installation of Screen steel casing Ǿ 8 5/8" | M | 51
4.1.4 | Supply and installation of ¾” class B observation pipe | M | 150
5 | Supply and pack river gravel (6-9mm diameter) | M3 | 18
6 | Well cleaning and development | Hr | 11
7 | Well head construction as per specification a concrete slab 0.5x0.5x0.50m (above ground) | ls | 1
8 | Grout the well up 6m depth 1;3 cement and sand mix | ls | 1
10 | PUMPING TEST
10.1 | Step drawdown test | Hr | 4
10.2 | Constant rate test | Hr | 72
10.3 | Recovery Monitoring | Hr | 24
11 | Chemical analysis | ls | 1
12 | Submit well completion report infives copies | ls | 1
TOTAL
VAT 15%
GRAND TOTAL
Notices:
- price of all material is calculated including transportation to the site
- point of borehole, working process and bore depth will be confirmed with clients expert/supervisor, who will be present in person during boring in the place
- client's supervisor may stop the drilling operations if in their opinion sufficient water supply has been obtained or further drilling is not promising for increasing the yield
- * works will be calculated according real amount (depth, quantity)

## Hamesho
Bill of Quantity for deep well drilling& construction Hamesho - 1. C
Zone: Sidama
Woreda :Bensa
Kebele: Hamesho
Estimated depth 150m
No | Description | Unit | Qty | Unit price | Total price
1 | General item
1.1 | inter site Mobilization of machineries , Equipment personal starting to woreta to Drilling site | km | 20
1.2 | Site clearing & rigging up prior to start drilling | ls | 1
1.3 | Demobilization of Manpower and equipment after finshing Hamesho site back to addis abeba | km | 430
2 | Drilling With Ǿ14"-Ǿ12"
2.1 | Drilling top part by Ǿ14" | M | 18
2.2 | Drilling in any formation by Ǿ12" Air DTH/Rotary Mud system | M | 132
3 | LOGGING
3.1 | Litho logic Logging | ls | 1
3.2 | Electrical Resistivity(long normal ,Short normal ,lateral | ls | 1 |  | Rate Only
4 | CONSTRUCTION
4.1 | Supply and installation
4.1.1 | Supply and installation of permanent steel casing for Ǿ 13 3/4" prevention of collapse | M | 18
4.1.2 | Supply and installation of Blind steel casing Ǿ 8 5/8" | M | 105
4.1.3 | Supply and installation of Screen steel casing Ǿ 8 5/8" | M | 45
4.1.4 | Supply and installation of ¾” class B observation pipe | M | 120
5 | Supply and pack river gravel (6-9mm diameter) | M3 | 20
6 | Well cleaning and development | Hr | 11
7 | Well head construction as per specification a concrete slab 0.5x0.5x0.50m (above ground) | ls | 1
8 | Grout the well up 6m depth 1;3 cement and sand mix | ls | 1
10 | PUMPING TEST
10.1 | Step drawdown test | Hr | 4
10.2 | Constant rate test | Hr | 72
10.3 | Recovery Monitoring | Hr | 24
11 | Chemical analysis | ls | 1
12 | Submit well completion report infives copies | ls | 1
TOTAL
VAT 15%
GRAND TOTAL
Notices:
- price of all material is calculated including transportation to the site
- point of borehole, working process and bore depth will be confirmed with clients expert/supervisor, who will be present in person during boring in the place
- client's supervisor may stop the drilling operations if in their opinion sufficient water supply has been obtained or further drilling is not promising for increasing the yield
- * works will be calculated according real amount (depth, quantity)